## EXAMPLE - Software Project Plan
SOFTWARE PROJECT PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS | GROUP MEMBERS
Culminating | Armin | 100% | 2025-06-03 | 2025-06-17 | 14 | Armin , Arsam
SCOPE DESCRIPTION
This project is a desktop-based multi-game suite developed using both the Ursina and Pygame engines, designed to deliver an engaging and fully graphical experience with no terminal-based interaction. Ursina was utilized for the Space Invaders game due to its efficient 3D rendering and intuitive game object management, Pygame was employed for classic 2D games like Tic Tac Toe, offering an amazing and simple to use event handling and multimedia capabilities. Each game launches in its own dedicated window, providing a consistent and user-friendly interface across the suite. The game features modules to support generalization and reusability followed by easy future expansion, with integrated background music and audio controls for a more exciting experience(the checkers game does not invlove music due to need of concentration). Overall, the suite represents an interactive gaming environment that prioritizes accessibility, maintainability, and high-quality design standards suitable for production-level deployment.
TASK NAME | ASSIGNED TO |  | START | FINISH | DAYS | STATUS | GANTT CHART
[7 empty] | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-03
Space_Invaders | Armin | Planned | 2025-06-07 | 2025-06-10 | 3 | COMPLETE
|  | Actual | 2025-06-07 | 2025-06-11 | 4
Tick-Tac-Toe | Armin | Planned | 2025-06-03 | 2025-06-05 | 2 | COMPLETE
|  | Actual | 2025-06-03 | 2025-06-04 | 1
Checkers | Arsam | Planned | 2025-06-07 | 2025-06-12 | 5 | COMPLETE
|  | Actual | 2025-06-07 | 2025-06-15 | 8
Menu | Armin , Arsam | Planned | 2025-06-05 | 2025-06-10 | 5 | COMPLETE
|  | Actual | 2025-06-05 | 2025-06-16 | 9

## EXAMPLE - Checklist Prior to Pr
CHECKLIST PRIOR TO PROJECT LAUNCH TEMPLATE
PROJECT NAME |  | DATE |  | PROJECT MANAGER
Culminating |  | 2025-06-17 |  | Armin
TASK CHECKLIST |  | STATUS | DATE | NOTES
TRUE | Doc string | RELEASED | 2025-06-16 | The code is well documented
TRUE | thoroghly and well documented | RELEASED | 2025-06-16 | The program is thoroghly documente in a comprehensive fasion
TRUE | submit all the fiels | RELEASED | 2025-06-16 | The whole project is submitted through GitHub
TRUE | Games require very clear win / lose conditions. | RELEASED | 2025-06-16 | the winning and losing conditions are mentioned in README.md and are completely functional in the program
TRUE | Unit tests | RELEASED | 2025-06-16 | we have tested everythin we can and there ae some things that weren't testable ( at least within our knowledge of unittests and testing)
TRUE | In-line, off-line and on-line comments | RELEASED | 2025-06-16 | The program is well commented
TRUE | Properly formatted code | RELEASED | 2025-06-16 | The program is well documented with well structured docstrings and comments
TRUE | Use of recursion | RELEASED | 2025-06-16 | Used multiple times including in the capturing algorithm and in the merge sort algorithm
TRUE | OOP: parent class, child class, methods, and operator overloading | RELEASED | 2025-06-16 | The program is mostly Object Oriented
TRUE | Using .txt files (as a score board) | RELEASED | 2025-06-16 | The txt file is used as a database for saving the wins for each color in checkers
TRUE | Modules: multiple files, importing | RELEASED | 2025-06-16 | The main goal was to have a modular architecture due to its reusability and accessability

## Project Performance Evaluation
PROJECT PERFORMANCE EVALUATION TEMPLATE
PROJECT NAME
Culminating
MEETING DATE
2025-06-16
MEETING TIME
18:16
FACILITATOR
Armin
ATTENDEES
Armin , Arsam
MEETING OBJECTIVES
Original Project Goal: State the project's scope of work and deliverables. Was the product delivered on time and to client satisfaction (Ms. Su's satisfaction)?
This project is a desktop-based multi-game suite developed using both the Ursina and Pygame engines, designed to deliver an engaging and fully graphical experience with no terminal-based interaction. Ursina was utilized for the Space Invaders game due to its efficient 3D rendering and intuitive game object management, Pygame was employed for classic 2D games like Tic Tac Toe, offering an amazing and simple to use event handling and multimedia capabilities. Each game launches in its own dedicated window, providing a consistent and user-friendly interface across the suite. The game features modules to support generalization and reusability followed by easy future expansion, with integrated background music and audio controls for a more exciting experience(the checkers game does not invlove music due to need of concentration). Overall, the suite represents an interactive gaming environment that prioritizes accessibility, maintainability, and high-quality design standards suitable for production-level deployment. One of the main goals was also to be able to program a game that would be delivered to a more broad audience in the future rather than just Ms.Su or the Computer Science class( although this might not be achievable in the timeline for this assignmenet but it will be done in the near future. The project was submitted on time to Ms. Su, despite being delivered later than what was initially planned by the group. This project was met by Ms.Su's(the client's) satisfaction in the demo deliveries and is aimed to be updated in the future to reach a more broad audience since this is a real-world project.
Timeline: Compare the initial schedule to the actual timeline. Were there events that impacted the schedule or team relationship?
Most of the initially planned timelines were met by the group despite not being able to reach the timeline at some parts of the project due to the expand of the project in the checkers game. Another event that impacted the schedule of the team was the fact that we were not as used to github as the team should have been. This brought us to deliver the game about 4-5 days after the initial timeline planned by us as a team. Disregarding that, in other aspects of the timeline, the project ran smoothly due to the fact that all of the work was planned and distributed equally to merge the whole project into one in a relatively realistic timeline. Therefore, although there were some problems with the timeline, the team is satisfied with the delivery timeline and the design.
TEAM DISCUSSION
Did we get our desired results?
As a team, we can agree that we did achieve our desired results, however, it definitely could have been a more smooth and enjoyable path than what the team experienced by having more team members and specialist working on the what we would call the visual effects and the visual design of the games since they consumed a huge amount of the team's time and ended up being just like the other games developed before which at this stage is more than enough but in real-world projects this would end up being a problem for the team. Despite that, the result met the initial plan, scope, and almost the timeline accurately. This included having 3D and 2D interactive visual effects and the project being useful in real-world applications.
What went well?
Several aspects of the project went well. First, the collaboration between team members was strong with each person contributing as much as possible in the poject and communicating to the best of their ability during the project. This included them completing their assigned tasks meaningfully, since responsibilities were clearly divided. The use of different engines and different games while using a lot of resources during the project and learning a lot (Ursina for Space Invaders and Pygame for the rest) was handled smoothly, showing our ability to manage technical diversity. The design remained fully window-based as planned. And, all of the games were completed successfully, having their features completely implemented and functional. Therefore communication, documentaiton , and adapting to changes went well.
What could've gone better?
There were some small areas where things could’ve gone better. Most importantly, the project timeline slipped for a few tasks which shows that time scheduling could be improved. Additionally, more frequent testing during the beginning stages of the game and earlier feedback sessions might have helped catch issues with each sections of the program earlier on, especially with different engines. Therefore our scheduling and the earlier testings could have gone better.
What could we do differently next time?
Looking back, we realize that we could have managed our time better and communicated more consistently, especially during our testings throughout the project. At the beginning, we underestimated how challenging the checkers game and the mixed game engine menu would be. We thought it would be more straightforward, but as we got to use them more and more we realized that there are a lot of debugging and testings that are required to be done for the project that we underestimated. This was due to lack of research about all of the python game egines and lack of previous knowledge about game developement, rendering, frames, etc. Therefore, for the next time( which unfortunately would be in university) we would try to have researched all of the topics that we would be working on beforehand so that we could come up with a better timeline and scheduling.

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS KEY | STATUS KEY
COMPLETE | RELEASED
IN PROGRESS | PLANNED
ON HOLD | ONGOING
OVERDUE
NOT STARTED